## Sprint Planning
Sprint No | Sprint Duration | Objective | Deliverables | Status
1 | Oct 10 - Oct 13, 2025 | Set up environment, collect dataset, and train YOLO model for helmet detection. | Helmet detection model, dataset ready. | Completed
2 | Oct 14 - Oct 17, 2025 | Integrate mobile phone detection and preprocessing pipeline using OpenCV. | Mobile detection integrated with existing pipeline. | Completed
3 | Oct 18 - Oct 22, 2025 | Add triple riding detection logic and generate violation CSV logs. | Triple riding violation detection implemented. | Completed
4 | Oct 23 - Oct 26, 2025 | Enhance UI, testing, and prepare project documentation and reports. | Dashboard and Agile documentation finalized. | Completed

## Daily Progress
Date | Task Planned | Progress Summary | Status
Oct 10 | Environment setup, dependency installation | Setup done successfully. | Done
Oct 11 | Dataset collection for helmet detection | Helmet dataset gathered. | Done
Oct 12 | YOLO model configuration and initial testing | YOLO detection functional. | Done
Oct 13 | Validation of helmet detection results | Helmet detection verified. | Done
Oct 14 | Add mobile phone detection pipeline | Mobile detection added. | Done
Oct 15 | Integrate detection with Flask backend | Flask connected successfully. | Done
Oct 16 | Debug model accuracy issues | Accuracy improved after tuning. | Done
Oct 17 | Finalize mobile violation results | Mobile violation verified. | Done
Oct 18 | Develop logic for triple riding detection | Triple riding logic implemented. | Done
Oct 19 | Integrate triple riding logic into backend | Integrated with backend. | Done
Oct 20 | Generate CSV reports for violations | CSV output verified. | Done
Oct 21 | UI update to show detected violations | UI functioning properly. | Done
Oct 22 | Testing complete module for all violations | All violations detected correctly. | Done
Oct 23 | UI polishing and error handling | UI improved with layout fix. | Done
Oct 24 | Documentation writing | Documentation 80% done. | Done
Oct 25 | Agile report preparation | Agile files created. | Done
Oct 26 | Final testing and submission | Project finalized and delivered. | Done

## Sprint Review
Sprint | Achievements | Challenges | Solutions/Improvements | Sprint Status
1 | Environment and helmet model setup done successfully. | Initial model accuracy issues. | Hyperparameter tuning fixed accuracy. | Completed
2 | Mobile violation detection integrated. | Dataset imbalance for mobile detection. | Added data augmentation to improve results. | Completed
3 | Triple riding detection working properly. | Detecting more than two persons accurately. | Implemented counting logic using bounding boxes. | Completed
4 | Documentation and dashboard finalized. | Minor UI bugs and final deployment. | UI tested across multiple images and fixed errors. | Completed

## Introspection
Aspect | Observation
Teamwork | Individual project managed effectively.
Technical Learning | Gained hands-on experience with YOLO, OpenCV, Flask.
Time Management | Completed all tasks within timeline (Oct 10–26).
Challenges Faced | Faced issues in triple riding logic and dataset availability.
Improvements Noted | Enhanced debugging and performance optimization skills.
Overall Outcome | Successfully built and demonstrated a working traffic violation detection system.