## Sheet1
Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
Helmet detection accuracy drops in night images | Sprint 1 | Bindu | Model Accuracy | Added night-time images for retraining | 20-Oct-2025 | Closed | Accuracy improved
Triple riding not detected for side view images | Sprint 1 | Bindu | Model Accuracy | Trained with more side-view data | 21-Oct-2025 | Closed | Side detection fixed
Mobile phone wrongly detected for pillion passengers | Sprint 2 | Bindu | False Detection | Adjusted bounding region to focus on driver only | 22-Oct-2025 | Closed | Now detects correctly
Bounding boxes overlap in crowded scenes | Sprint 2 | Bindu | UI/Display | Modified display coordinates to avoid overlap | 23-Oct-2025 | Closed | Boxes displayed properly
Results not saving into CSV occasionally | Sprint 2 | Bindu | Logic Error | Fixed file writing logic | 24-Oct-2025 | Closed | Saved successfully
UI freezes when large video is uploaded | Sprint 3 | Bindu | Performance | Optimized frame extraction process | 25-Oct-2025 | Closed | No lag observed
Red signal detection prototype fails on blurred frames | Sprint 3 | Bindu | Model Accuracy | Improved thresholding for red detection | 26-Oct-2025 | Closed | Prototype stable
Detection delay observed during multiple model runs | Sprint 3 | Bindu | Performance | Reduced model size and used threading | 27-Oct-2025 | Closed | Processing faster
Mobile detection confused with other handheld items | Sprint 4 | Bindu | False Detection | Filtered out irrelevant handheld objects | 28-Oct-2025 | Closed | False positives reduced
Low confidence score for small helmets | Sprint 4 | Bindu | Model Confidence | Improved detection layer for small helmets | 29-Oct-2025 | Closed | Confidence scores improved