## Sheet1
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a user, I want to upload an image/video for violation detection | Must | None | Bindu | Completed
Sprint 2 | Sprint 2 | US002 | As a system, I should detect helmet violations accurately | Must | US001 | Bindu | Completed
Sprint 2 | Sprint 2 | US003 | As a system, I should detect mobile phone usage while driving | Should | US001 | Bindu | Completed
Sprint 3 | Sprint 3 | US004 | As a system, I should detect triple riding violations | Could | US002 | Bindu | Completed
Sprint 3 | Sprint 3 | US005 | As a user, I should be able to view results and save them | Must | US001 | Bindu | Completed
Sprint 3 | Sprint 3 | US006 | As a system, I should display multiple violations clearly | Should | US002 | Bindu | Completed